## Client
PLUR Enterprise — Offer
Parameters (adjust yellow cells)
| Number of seats | 50
| List price per seat (EUR/month) | 70
| Founding Partner discount | 30%
| Consulting rate (EUR/hour) | 85
| Subscription commitment (months) | 12
Team
| Gregor | Project Director, Lead Dev
| Tadej | CTO, Tech Lead
| Marko | DevOps
| Crt | PM, Data Scientist
Timeline
| When |  | Milestone |  | Details
| Early May |  | Contract signed
| May W1–2 |  | Integration + first 5 repos |  | GitLab SSO, deployment in parallel with scanning first 5 repos
| May W2–3 |  | Feedback loop |  | Present results to tech leads, tune extraction pipeline
| May W3–4 |  | Test run + next batch |  | Infra live, 10-15 users collecting memories. Scan next 10-15 repos with tuned pipeline.
| June |  | Onboarding month — subscription starts |  | 50 users, setup workshop. 20-30 repos curated, packs deployed.
| June–July |  | Knowledge Engineering Phase A completes |  | Remaining active repos, pipeline refinement
| July–Aug |  | Knowledge Engineering Phase B |  | 1,370 repos automated, new project hook, coverage report, handover
| Q3/Q4 2026 |  | Datacore Enterprise (scoped together) |  | AI Development Team — Chief of Staff, Insight Agent, Onboarding Companion
Subscription starts at go-live (June 2026), not at contract signing.
Integration + test run (May) included — no subscription charges before go-live.
1. PLUR ENTERPRISE — Organizational Learning (subscription)
List price per seat
Founding Partner price per seat
| Monthly subscription |  |  |  | seats × price =
Annual commitment
Annual savings vs list price
What’s included:
1 | PLUR Enterprise server (HTTP/SSE MCP, multi-user)
2 | PostgreSQL + AGE (knowledge graph) + pgvector (semantic search)
3 | SSO integration (configured for your identity provider)
4 | Scope-based access control + role-level permissions
5 | MCP tool security (allowlist, write enforcement, audit)
6 | Admin dashboard (usage, health, audit log)
7 | Deployment, TLS, CI/CD, monitoring & alerting
8 | Security patches, dependency updates, platform upgrades
9 | Infrastructure hosting & AI compute (included)
10 | Priority bug fixes (< 24h response, < 72h resolution)
11 | Weekly check-in + quarterly strategic review
Market context:
| GitHub Copilot Enterprise |  |  | $39-60/seat/mo | Code completion, 28-day memory, no learning
| Augment Code Standard |  |  | $60/seat/mo | Project memory, no correction-based learning
| Sourcegraph Cody Enterprise |  |  | $59/seat/mo | Code search, no persistent memory
| JetBrains AI Enterprise |  |  | $60+/seat/mo | IDE AI features, no org memory
| PLUR Enterprise (list) |  |  | €70/seat/mo | Persistent org learning, correction-based, knowledge graph
| PLUR Enterprise (Founding Partner) |  |  | €49/seat/mo | Same — 30% Founding Partner discount
2. KNOWLEDGE ENGINEERING (one-time project)
Scan your codebase, extract conventions, build your custom ingest pipeline
# | Deliverable | Gregor | Tadej | Marko | Crt | Total h | Cost (EUR)
Integration — GitLab & Deployment
1 | GitLab OAuth2/OIDC + PKCE integration |  | 16
2 | GitLab group/project membership sync & webhooks |  | 12
3 | Deployment & configuration for your GitLab instance |  | 4 | 8
4 | Setup workshop (all hands, 2-3h) | 4 |  |  | 4
5 | Project management & weekly check-ins (across all phases) |  |  |  | 16
Subtotal — Integration
| AI compute (tokens) | [5 empty] | 200
Phase A — 30 Active Repos (high-touch curation)
1 | Extraction strategy & planning with your tech leads |  |  |  | 8
2 | Convention extraction & analysis (30 repos, multiple passes) | 4 |  |  | 24
3 | Engram generation + quality tuning with your tech leads | 8 |  |  | 16
4 | Knowledge pack curation (per-project + per-group) | 4 |  |  | 12
5 | Custom ingest pipeline development (reusable for Phase B) |  | 16 |  | 4
6 | Phase report & deliverables review |  |  |  | 6
Subtotal — Phase A
| AI compute (tokens) | [5 empty] | 600
Phase B — 1,370 Repos (automated processing)
1 | Batch processing — run pipeline on all remaining repos |  |  |  | 12
2 | Quality review & outlier handling | 4 |  |  | 8
3 | New project hook (auto-extraction on repo creation via CI) |  | 8 | 8
4 | Coverage report & final handover |  |  |  | 6
Subtotal — Phase B
| AI compute (tokens) | [5 empty] | 400
KNOWLEDGE ENGINEERING TOTAL
Deliverables:
Custom ingest pipeline tuned to your codebase (reusable, automated)
30 active repos: curated knowledge packs, reviewed with your tech leads
1,370 repos: auto-processed, coverage report
New project hook: every new repo auto-bootstrapped on creation
3. DATACORE ENTERPRISE — AI Development Team (Founding Partnership continues)
Autonomous AI agents powered by your organizational learning. Separate product, same partnership. Scoped together after PLUR is in place.
| AI Role |  |  |  | Description |  | Indicative
| AI Chief of Staff |  |  |  | Org-wide operational intelligence — answers any question about your repos, decisions, team activity |  | 800
| Insight Agent |  |  |  | Proactive pattern detection — surfaces what you didn’t know to ask across teams |  | 600
| Onboarding Companion |  |  |  | Interactive guide for new developers — built from your actual conventions |  | 400
Pricing model: monthly per AI role. Exact scope determined together after Phase 1+2.
Founding Partnership discount applies to Datacore on same terms as PLUR.
FIRST-YEAR COMMITMENT
PLUR Enterprise subscription (12 months, Founding Partner rate)
Knowledge Engineering (custom project, standard rate)
FIRST-YEAR TOTAL
Monthly equivalent
vs list price (no Founding Partner discount)
Your savings as Founding Partner
ROI ESTIMATE
| Developer time searching for information (McKinsey) | [5 empty] | 1.8 hours/day
| Context switching cost per developer/year | [5 empty] | ~€50,000
Conservative: saving 15 min/day per developer
Annual recovered value
ROI (recovered value / investment)
Break-even (months)
Design Partner Benefits
30% Founding Partner discount on PLUR Enterprise subscription
Guaranteed best rate — you will never pay more than any future customer
Influence on product roadmap — your requirements built first
White-label & reseller rights (pre-negotiated for future)
Partnership continues with Datacore Enterprise on same terms
Case study & reference customer agreement
Integration phase included — no charges before go-live
Weekly check-ins + quarterly strategic reviews
Notes
All prices exclude VAT.
Subscription: 12-month commitment starting at go-live (June 2026). No charges during integration.
Founding Partner rate: guaranteed best rate — you will never pay more than any future customer.
Knowledge Engineering: invoiced on actuals at standard consulting rate, with weekly reporting.
Datacore Enterprise (AI Development Team): scoped and priced as monthly AI roles after PLUR is in place.
GitHub provider available as future add-on when needed.
We use Claude Code and AI-assisted development — this is how we deliver fast.
Yellow cells are adjustable — all totals recalculate automatically.
ROI based on McKinsey research (1.8h/day searching) and GitHub/Accenture productivity studies (25-55% gain).

## Internal
PLUR Enterprise — Offer (INTERNAL)
Parameters (adjust yellow cells)
| Number of seats | 50
| List price per seat (EUR/month) | 70
| Founding Partner discount | 30%
| Consulting rate (EUR/hour) | 85
| Subscription commitment (months) | 12
| Internal team rate (EUR) | 60
| Platform internal cost (mostly built) | 3000
Team
| Gregor | Project Director, Lead Dev
| Tadej | CTO, Tech Lead
| Marko | DevOps
| Crt | PM, Data Scientist
Timeline
| When |  | Milestone |  | Details
| Early May |  | Contract signed
| May W1–2 |  | Integration + first 5 repos |  | GitLab SSO, deployment in parallel with scanning first 5 repos
| May W2–3 |  | Feedback loop |  | Present results to tech leads, tune extraction pipeline
| May W3–4 |  | Test run + next batch |  | Infra live, 10-15 users collecting memories. Scan next 10-15 repos with tuned pipeline.
| June |  | Onboarding month — subscription starts |  | 50 users, setup workshop. 20-30 repos curated, packs deployed.
| June–July |  | Knowledge Engineering Phase A completes |  | Remaining active repos, pipeline refinement
| July–Aug |  | Knowledge Engineering Phase B |  | 1,370 repos automated, new project hook, coverage report, handover
| Q3/Q4 2026 |  | Datacore Enterprise (scoped together) |  | AI Development Team — Chief of Staff, Insight Agent, Onboarding Companion
Subscription starts at go-live (June 2026), not at contract signing.
Integration + test run (May) included — no subscription charges before go-live.
1. PLUR ENTERPRISE — Organizational Learning (subscription)
List price per seat
Founding Partner price per seat
| Monthly subscription |  |  |  | seats × price =
Annual commitment
Annual savings vs list price
What’s included:
1 | PLUR Enterprise server (HTTP/SSE MCP, multi-user)
2 | PostgreSQL + AGE (knowledge graph) + pgvector (semantic search)
3 | SSO integration (configured for your identity provider)
4 | Scope-based access control + role-level permissions
5 | MCP tool security (allowlist, write enforcement, audit)
6 | Admin dashboard (usage, health, audit log)
7 | Deployment, TLS, CI/CD, monitoring & alerting
8 | Security patches, dependency updates, platform upgrades
9 | Infrastructure hosting & AI compute (included)
10 | Priority bug fixes (< 24h response, < 72h resolution)
11 | Weekly check-in + quarterly strategic review
Market context:
| GitHub Copilot Enterprise |  |  | $39-60/seat/mo | Code completion, 28-day memory, no learning
| Augment Code Standard |  |  | $60/seat/mo | Project memory, no correction-based learning
| Sourcegraph Cody Enterprise |  |  | $59/seat/mo | Code search, no persistent memory
| JetBrains AI Enterprise |  |  | $60+/seat/mo | IDE AI features, no org memory
| PLUR Enterprise (list) |  |  | €70/seat/mo | Persistent org learning, correction-based, knowledge graph
| PLUR Enterprise (Founding Partner) |  |  | €49/seat/mo | Same — 30% Founding Partner discount
2. KNOWLEDGE ENGINEERING (one-time project)
Scan your codebase, extract conventions, build your custom ingest pipeline
# | Deliverable | Gregor | Tadej | Marko | Crt | Total h | Cost (EUR)
Integration — GitLab & Deployment
1 | GitLab OAuth2/OIDC + PKCE integration |  | 16
2 | GitLab group/project membership sync & webhooks |  | 12
3 | Deployment & configuration for your GitLab instance |  | 4 | 8
4 | Setup workshop (all hands, 2-3h) | 4 |  |  | 4
5 | Project management & weekly check-ins (across all phases) |  |  |  | 16
Subtotal — Integration
| AI compute (tokens) | [5 empty] | 200
Phase A — 30 Active Repos (high-touch curation)
1 | Extraction strategy & planning with your tech leads |  |  |  | 8
2 | Convention extraction & analysis (30 repos, multiple passes) | 4 |  |  | 24
3 | Engram generation + quality tuning with your tech leads | 8 |  |  | 16
4 | Knowledge pack curation (per-project + per-group) | 4 |  |  | 12
5 | Custom ingest pipeline development (reusable for Phase B) |  | 16 |  | 4
6 | Phase report & deliverables review |  |  |  | 6
Subtotal — Phase A
| AI compute (tokens) | [5 empty] | 600
Phase B — 1,370 Repos (automated processing)
1 | Batch processing — run pipeline on all remaining repos |  |  |  | 12
2 | Quality review & outlier handling | 4 |  |  | 8
3 | New project hook (auto-extraction on repo creation via CI) |  | 8 | 8
4 | Coverage report & final handover |  |  |  | 6
Subtotal — Phase B
| AI compute (tokens) | [5 empty] | 400
KNOWLEDGE ENGINEERING TOTAL
Deliverables:
Custom ingest pipeline tuned to your codebase (reusable, automated)
30 active repos: curated knowledge packs, reviewed with your tech leads
1,370 repos: auto-processed, coverage report
New project hook: every new repo auto-bootstrapped on creation
3. DATACORE ENTERPRISE — AI Development Team (Founding Partnership continues)
Autonomous AI agents powered by your organizational learning. Separate product, same partnership. Scoped together after PLUR is in place.
| AI Role |  |  |  | Description |  | Indicative
| AI Chief of Staff |  |  |  | Org-wide operational intelligence — answers any question about your repos, decisions, team activity |  | 800
| Insight Agent |  |  |  | Proactive pattern detection — surfaces what you didn’t know to ask across teams |  | 600
| Onboarding Companion |  |  |  | Interactive guide for new developers — built from your actual conventions |  | 400
Pricing model: monthly per AI role. Exact scope determined together after Phase 1+2.
Founding Partnership discount applies to Datacore on same terms as PLUR.
FIRST-YEAR COMMITMENT
PLUR Enterprise subscription (12 months, Founding Partner rate)
Knowledge Engineering (custom project, standard rate)
FIRST-YEAR TOTAL
Monthly equivalent
vs list price (no Founding Partner discount)
Your savings as Founding Partner
ROI ESTIMATE
| Developer time searching for information (McKinsey) | [5 empty] | 1.8 hours/day
| Context switching cost per developer/year | [5 empty] | ~€50,000
Conservative: saving 15 min/day per developer
Annual recovered value
ROI (recovered value / investment)
Break-even (months)
MARGIN ANALYSIS (INTERNAL ONLY)
Subscription revenue (12 months)
Subscription cost (platform + ~8h/mo support)
Subscription margin
Knowledge Engineering revenue
Knowledge Engineering cost (hours × internal rate)
Knowledge Engineering margin
TOTAL FIRST-YEAR MARGIN
Margin % on revenue
Design Partner Benefits
30% Founding Partner discount on PLUR Enterprise subscription
Guaranteed best rate — you will never pay more than any future customer
Influence on product roadmap — your requirements built first
White-label & reseller rights (pre-negotiated for future)
Partnership continues with Datacore Enterprise on same terms
Case study & reference customer agreement
Integration phase included — no charges before go-live
Weekly check-ins + quarterly strategic reviews
Notes
All prices exclude VAT.
Subscription: 12-month commitment starting at go-live (June 2026). No charges during integration.
Founding Partner rate: guaranteed best rate — you will never pay more than any future customer.
Knowledge Engineering: invoiced on actuals at standard consulting rate, with weekly reporting.
Datacore Enterprise (AI Development Team): scoped and priced as monthly AI roles after PLUR is in place.
GitHub provider available as future add-on when needed.
We use Claude Code and AI-assisted development — this is how we deliver fast.
Yellow cells are adjustable — all totals recalculate automatically.
ROI based on McKinsey research (1.8h/day searching) and GitHub/Accenture productivity studies (25-55% gain).
INTERNAL SHEET — do not share with client.