## Cost Breakdown
PLUR Enterprise — Cost Breakdown
Parameters (adjust yellow cells)
| Hourly rate (EUR) | 85
| Design partner discount | 20%
| Monthly support retainer (EUR) | 2500
| Monthly token budget (EUR) | 150
| Monthly infrastructure (EUR) | 100
| Support months in year 1 | 9
Team
| Gregor | Project Director, Lead Dev
| Tadej | CTO, Tech Lead
| Marko | DevOps
| Crt | PM, Data Scientist
PROJECT DELIVERY
# | Deliverable | Gregor | Tadej | Marko | Crt | Total h | Cost (EUR)
Phase 1 — Shared Memory (50 users)
1 | PostgreSQL backend with graph (AGE) + vector search | 8 | 20 | 4
2 | Multi-user MCP server (HTTP/SSE transport) | 4 | 16
3 | GitLab SSO integration (OAuth2/OIDC + PKCE) |  | 20
4 | Scope-based access control + role-level permissions |  | 24
5 | MCP tool security (allowlist, write enforcement) | 4 | 12
6 | Structured logging, audit trail & PII handling |  | 8 | 4
7 | Admin dashboard (usage, health, audit log) | 24 | 8
8 | Monitoring & alerting |  |  | 12
9 | Server deployment (TLS, CI/CD, backups) |  | 4 | 16
10 | IDE compatibility validation & documentation |  | 4 |  | 8
11 | Onboarding all 50 users | 4 |  |  | 12
Subtotal — Phase 1
| AI compute (tokens) | [5 empty] | 1450
Phase 2 — Knowledge Engineering
1 | Repo scanning pipeline (1,400 repos — configs, CI, docs) |  | 8 |  | 16
2 | Convention & pattern extraction engine |  | 8 |  | 20
3 | Engram generation + quality tuning (multiple passes) | 8 |  |  | 12
4 | Knowledge pack packaging (per-project, per-group, org) |  | 8 |  | 8
5 | Review & curation workflow with tech leads | 8 |  |  | 8
6 | Quality feedback loop (signals tune extraction) |  | 4 |  | 8
7 | New project hook (auto-extraction on repo creation) |  | 8 | 8
Subtotal — Phase 2
| AI compute (tokens) | [5 empty] | 580
Phase 3 — AI Development Team (Datacore Enterprise)
1 | AI Chief of Staff — org-wide operational intelligence | 8 | 16 |  | 4
2 | Insight Agent — proactive pattern detection & recommendations | 8 | 12 |  | 8
3 | Onboarding Companion — interactive guide for new developers | 4 | 12 |  | 8
4 | Orchestration engine (task queue, routing, quality gates) | 16 | 20
5 | GitLab CI/CD integration (agents triggered from pipelines) |  | 8 | 8
6 | Dashboard (execution monitoring, success rates, cost) | 12 | 8
7 | Workflow discovery & configuration with client | 4 |  |  | 8
Subtotal — Phase 3
| AI compute (tokens) | [5 empty] | 870
Add-on — GitHub Provider (when needed)
1 | GitHub SSO integration (OAuth + org sync) |  | 16
2 | GitHub webhook handler + membership sync |  | 8 | 4
Subtotal — Add-on
| AI compute (tokens) | [5 empty] | 0
PROJECT TOTAL
Design partner discount
PROJECT DELIVERY (design partner price)
MONTHLY SUPPORT & MAINTENANCE
| Included in monthly retainer | [5 empty] | Monthly
1 | Security patches, dependency updates & PLUR core upgrades
2 | Infrastructure monitoring, uptime SLA (99.5%), incident response
3 | Knowledge pipeline tuning (extraction quality, pack curation)
4 | New user onboarding (team growth, offboarding cleanup)
5 | Priority bug fixes (< 24h response, < 72h resolution)
6 | Platform evolution (new MCP clients, IDE support, model changes)
7 | AI compute (token budget for agents, extraction, orchestration)
8 | Quarterly review & optimization session
MONTHLY RETAINER (50 users)
Annual support cost
Support starts after Phase 1 delivery
FIRST-YEAR ENGAGEMENT SUMMARY
Project delivery (Phases 1-3, design partner price)
Support & maintenance (starts after Phase 1)
Infrastructure (hosting, database — at cost)
FIRST-YEAR TOTAL
Payment Schedule
| Phase 1 — Shared Memory | Months 1-2
| Phase 2 — Knowledge Engineering | Months 2-4
| Phase 3 — AI Development Team | Months 4-6
| Add-on — GitHub Provider | When needed
| Monthly support (ongoing) | From month 3
Team Utilization
Gregor (Project Director, Lead Dev)
Tadej (CTO, Tech Lead)
Marko (DevOps)
Crt (PM, Data Scientist)
Design Partner Benefits
Influence on product roadmap — your requirements built first
White-label & reseller rights (future phase, pre-negotiated)
Case study & reference customer agreement
Priority support with dedicated team
Quarterly product review & roadmap alignment sessions
Notes
All prices exclude VAT.
Project hours invoiced on actuals with weekly reporting.
Design partner pricing valid for 12 months from contract start.
Infrastructure costs (DO droplet, managed Postgres) billed at cost.
Support retainer covers up to 50 users. Additional users: 30 EUR/user/month.
We use Claude Code and AI-assisted development extensively — this is how we deliver fast.
Yellow cells are adjustable — all totals recalculate automatically.